## Wildcat Gulch
Project Checklist for Phase 2 2013 Flood EWP:
Watershed:
Project:
DSR Construction Estimate:
EWP Program Management Use Only:
Date Completed | Responsible Party | Task Description | Deliverable | Task Complete | Verification By | Additional Notes
Completed before contract development of 30 percent design.
| Local Sponsor/CWCB | Project Kickoff Meeting with CWCB. | Meeting minutes from Kickoff meeting or supporting documentation that meeting was held with CWCB or CWCB representative.
| Local sponsor | Landowner permission- Landowner permissions slips must be signed for all landowners that has property within the project work area(s). (A standard form is being developed for the watersheds. Local sponsors may require a different form that meets the requirement.) | 1. Parcel/ownership map in project area showing impacted properties. 2. Landowner permission letter or equivalent for each affected property.
| Local sponsor | Local Sponsor letter of intent - Sponsor needs to show the willingness to pay 12.5 percent of the implementation cost. A breakdown of cash, material and volunteer hours is needed. (Remember, no cost can be incurred until a CWCB/NRCS Financial Agreement is signed). | Letter of intent on sponsor letterhead containing information noted.
| NRCS | DSR is complete. | DSR
Need before construction – These items are being completed during 30 percent design
| NRCS/CWCB | Biological Assessment - NRCS/CWCB will complete this as a portion of the DSR. | BA is included in DSR. Lettter from USFWS will be included as part of the checklist package.
| CWCB | Cultural Resources - This will be completed as part of 30% design. CWCB will complete this work whether local sponsor or CWCB TA team is completing the work.
| Local sponsor | Permits: The sponsor is required to obtain all permits for the project. | List of local permits required for the project (developed by sponsor).
| Local sponsor | Local Permits (Please list all that are required/obtained) | Copy of all permit appplications and approvals from local and state agencies.
Permit 1:
Permit 2:
Permit 3:
| Local sponsor | State Permits (Please list all that are obtained)
CDPHE Construction Stormwater
Permit 2:
Permit 3:
| Local sponsor | Federal Permits (Please list all that are obtained)
|  | USACE 404 Permit | Letter from the Corps acknowledging project review and coverage under NW 37.
|  | FEMA CLOMR/LOMR | Letter from FEMA for Conditional Letter of Map Revision.
| Local sponsor | Coordination for relocation of utilities when applicable. Note utility and agency for each utility to be relocated: | 1. Letter stating that there are no known utility relocations needed with the project, or 2. List of utilities, agencies, and facility to be relocated including funding source and schedule for relocation.
Utility 1:
Utility 2:
Utility 3:
| Local Sponsor or CWCB TA Team | Develop a Quality Assurance Plan for Review by NRCS and CWCB | Quality assurance plan provided by sponsor.
| Local Sponsor or CWCB TA Team | O&M Plans for projects that have structural elements. Document plan has been reviewed by NRCS. | O&M plan
The following is in CDBG-DR 30% DESIGN GUIDELINES FOR PLAN DEVELOPMENT
| Local Sponsor or CWCB TA Team | Preliminary Basis of Design Report -- explains and documents hydrology, hydraulics, sediment transport, geomorphic features, and ecology and provides support for the selection, layout, and size of each design component. Typically includes: • Hydrology/Hydraulics data: preliminary models, results, and supporting electronic files (models, AutoCAD, and GIS) • Geomorphological data: cross-sections, pebble counts, photos • Sediment Transport Analysis: preliminary results and supporting data | Design report meeting requirements of Emergency Watershed Protection (EWP) Program, 2013 Colorado Recovery Phase 2, Project Engineering Guidance and providing information noted under task description.
| Local Sponsor or CWCB TA Team | • Existing conditions plan (base map) • Proposed conditions plan • Channel profile and cross sections • Detail drawings | Design plans providing required information noted under task description.
| Local Sponsor or CWCB TA Team | Draft Planting Plan: Planimetric map, spreadsheet estimate of plants and quantities • Permit Plan: Summary of permits, contacts, and estimated schedule • Draft Monitoring Plan: monitoring parameters/methods/frequency/responsible party timeline, suggested monitoring locations map. • Opinion of probable costs | Draft planing plan, permit plan, monitioring plan, and opinion of probable costs as noted under task description.
Final Plan Checklist
| NRCS | Project designs, drawings and specifications meets NRCS standards and technical criteria. Functional review has been completed by NRCS State Conservation Engineer. | 1. Functional review signed by NRCS 2. Technical review signed by CWCB.
| CWCB | Agreement signed between CWCB and local sponsor | Signed agreement.
| NRCS | Financial Agreement signed between CWCB and NRCS | Signed and executed FA agreement.
| Local Sponsor | ADS-78 form(s), Assurances Relating to Real Property Acquisition, to the NRCS Program Manager. An attorney’s opinion must be attached to the form certifying an examination of the real property instruments and files was made and found to provide adequate land title, rights, permission and authority for the purpose(s) of the project. | Completed ADS-78 form(s)
Construction
| CWCB | Within (10) calendar days of signing this project agreement, hold a project management conference with NRCS. | Meeting minutes from project management conference.
| Local sponsor | Provide a qualified and capable person to conduct construction inspection, and ensure compliance with the Quality Assurance Plan. | Provide construction oversight contact information.
| CWCB | Schedule a final inspection to include local sponsor, CWCB, contractor, design engineer, and NRCS representative. Document deficiencies and follow-up on correction. | Punchlist letter from NRCS/CWCB and letter documenting completion of all punchlist items.
Post Construction: See Emergency Watershed Protection (EWP) Program; 2013 Colorado Flood Recovery Phase 2; PROJECT ENGINEERING GUIDANCE for more guidance.
| Local Sponsor or CWCB TA Team | As built drawings were prepared as required | As-builts stamped by a PE.
| CWCB | Sign off for proper approval and PE signature | Letter from CWCB
Financial Agreement Close-out
| NRCS | Project Agreement Fulfilled:
| NRCS | EWP Funds Reconciled:
| NRCS | Final EWP Report Sent:
| All | Retain project documentation, agreements, permits, and other related information in a project file.