## CWCB Invoice Spreadsheet
XXX Project Invoice #:
Task | Task Description | Vendor Name | Vendor Invoice # | Total Project Budget | Invoice Total | NRCS Funds (max 75%) | CWCB Funds (12.5%) | NRCS+CWCB | Local Match (12.5%)
1 |  |  |  |  | 100 | 75 | 12.5 | 87.5 | 12.5
1 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1 |  |  |  |  | 0 | 0 | 0 | 0 | 0
2 |  |  |  |  | 0 | 0 | 0 | 0 | 0
2 |  |  |  |  | 0 | 0 | 0 | 0 | 0
2 |  |  |  |  | 0 | 0 | 0 | 0 | 0
3 |  |  |  |  | 0 | 0 | 0 | 0 | 0
3 |  |  |  |  | 0 | 0 | 0 | 0 | 0
3 |  |  |  |  | 0 | 0 | 0 | 0 | 0
4 |  |  |  |  | 0 | 0 | 0 | 0 | 0
4 |  |  |  |  | 0 | 0 | 0 | 0 | 0
4 |  |  |  |  | 0 | 0 | 0 | 0 | 0
5 |  |  |  |  | 0 | 0 | 0 | 0 | 0
5 |  |  |  |  | 0 | 0 | 0 | 0 | 0
5 |  |  |  |  | 0 | 0 | 0 | 0 | 0
6 |  |  |  |  | 0 | 0 | 0 | 0 | 0
6 |  |  |  |  | 0 | 0 | 0 | 0 | 0
6 |  |  |  |  | 0 | 0 | 0 | 0 | 0
6 |  |  |  |  | 0 | 0 | 0 | 0 | 0
6 |  |  |  |  | 0 | 0 | 0 | 0 | 0
6 |  |  |  |  | 0 | 0 | 0 | 0 | 0
6 |  |  |  |  | 0 | 0 | 0 | 0 | 0
Total |  |  |  |  | 100 | 75 | 12.5 | 87.5 | 12.5

## Invoice # Cover
PERIODIC ESTIMATE FOR PARTIAL PAYMENT
SUMMARY AND APPROVALS
PERIODIC ESTIMATE NO. # - PERIOD XXXX, 2017 THROUGH XXXXXX, 2017
PROJECT: | EWP/DR Project Name |  | CONTRACT NO: | 17-#####
CONTRACTOR: | Contractor Name |  | ACCOUNT NO: | ######
ADDRESS: | Street Name |  | FA NUMBER: | ######
| City, State, Zip |  | DR NUMBER: | #######
1. ANALYSIS OF ADJUSTED CONTRACT AMOUNT TO DATE:
a. Original Contract Price (column 6) |  |  |  | 0
b. Total of Change Order Additions or Deductions (column 18) |  |  |  | 0
c. Adjusted Contract Amount To Date |  |  |  | 0
2. ANALYSIS OF WORK PERFORMED TO DATE:
a. Cost of Original Contract Work Completed To Date (column 10) |  |  |  | 0
b. Extra Work Performed To Date, Minus Any Deductions (column 22) |  |  |  | 0
c. Total Cost of Work Performed To Date (2a + 2b) |  |  |  | 0
d. Retainage Per Contract Terms (2c x __%) |  |  |  | 0
e. Net Amount Earned On Contract Work To Date (2c. - 2d.) |  |  |  | 0
f. Add: Materials Stored This Period (column 34) |  |  |  | 0
g. Subtotal (2e + 2f) |  |  |  | 0
h. Less Amount of Previous Payments |  |  |  | 0
i. Less Additional Withholdings Per Contract Documents (Refer to Exhibit_ Attached)
j. Less Liquidated Damages (Refer to Exhibit_ Attached)
k. BALANCE DUE to Contractor for this Partial Payment or Final Payment (2g. - 2h. - 2i. - 2j.) |  |  |  | 0
CERTIFICATION OF CONTRACTOR:
According to the best of my knowledge and belief, I certify that all items and amounts shown on this Partial Payment or Final Payment are correct; that all work has been performed and/or material supplied in full accordance with the requirements of the referenced Contract, and/or duly authorized deviations, substitutions, alterations, and/or additions; that the foregoing is a true and correct statement of the Contract amount up to and including the last day of the period covered by this Partial Payment or Final Payment; that, for Partial Payments, no part of the BALANCE DUE (2, line "k") has been received, and that the undersigned and his subcontractors have no unpaid accounts for labor, material, equipment or subcontract services which have been due and payable for over 60 days except as follows: __________________. That, for Final Payment, no part of the BALANCE DUE amount has been received and that said BALANCE DUE amount is final and that the undersigned has paid in full all amounts due to any of his subcontractors for labor, materials, equipment, or work. Contractor, upon receipt of the BALANCE DUE set forth above from Owner, acknowledges payment in full of all sums due on account of labor, materials, supplies and other lienable items furnished by Contractor for the project on or prior to the date of this Partial Payment or Final Payment. Further, Contractor hereby waives and releases all claims Contractor may have under applicable law in lieu of the mechanic's lien laws or otherwise, on account of such labor, materials, supplies and other lienable items provided on or prior to the date of this Partial Payment or Final Payment.
By:_____________________________________ |  | Title:__________________________________ | Name:_______________________
Contractor |  |  | Print
Date:__________________________________
PERIODIC ESTIMATE FOR PARTIAL PAYMENT
SUMMARY AND APPROVALS
PERIODIC ESTIMATE NO. # - PERIOD XXXX, 2017 THROUGH XXXXXX, 2017
APPROVALS
To the best of our knowledge and belief, the above payment request is a fair estimate of the work completed for the period claimed, and no unauthorized deviation from the drawings and specifications covering the work which the Owner's Representative is under agreement to inspect, is included in the work for which payment is claimed. Recommendation for this payment does not constitute final acceptance of any of the work for which payment is requested and is not a waiver of any right the Owner has under the Contractor's agreement, general conditions, special conditions or technical specification.
RECOMMENDED FOR PAYMENT:
By:
Signature Sponsor's Engineer
______________________________________
Print Name Sponsor's Engineer
Date:
APPROVED FOR PAYMENT:
By:
Signature Sponsor Representative's Name
______________________________________
Print Sponsor Representative's Name
Date:

## Original Contract Work
PERIODIC ESTIMATE FOR PARTIAL PAYMENT
SUMMARY AND APPROVALS
PERIODIC ESTIMATE NO. # - PERIOD XXXX, 2017 THROUGH XXXXXX, 2017
ORIGINAL CONTRACT WORK
|  | ORIGINAL CONTRACT WORK |  |  |  | THIS PAY PERIOD |  | COMPLETED TO DATE
Bid Item | Description | Quantity | Pay Unit | Unit Price | Total Cost | Quantity | Total Cost | Quantity | Total Cost | Percent Complete
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11)
TASK 1 - REMOVALS AND RELOCATIONS
1 | Clearing and Grubbing | 0 | Acre | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
2 | Removal of Debris | 0 | Load | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
3 | Removal of Tree | 0 | EA | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
4 | Reset Pedestrian Footbridge | 0 | EA | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
5 | Reset Fence | 0 | LF | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
^^^^^^^^^^^^^INSERT ADDITIONAL PAY ITEMS ABOVE THIS LINE^^^^^^^^^^^^^^^
Task Subtotal |  |  |  |  | 0 |  | 0 |  | 0 | #DIV/0!
TASK 2 - EARTHWORK AND GRADING
6 | Unclassified Excavation (Complete in Place) | 0 | CY | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
7 | Topsoil | 0 | CY | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
8 | Stockpile Topsoil | 0 | CY | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
^^^^^^^^^^^^^INSERT ADDITIONAL PAY ITEMS ABOVE THIS LINE^^^^^^^^^^^^^^^
Task Subtotal |  |  |  |  | 0 |  | 0 |  | 0 | #DIV/0!
TASK 3 - EROSION CONTROL
9 | Site Erosion Control | 0 | LS | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
10 | Vehicle Tracking Pad | 0 | SY | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
11 | Stabilized Staging Area | 0 | SY | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
12 | Dewatering/Water Control | 0 | LS | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
13 | Fence (Plastic) (Construction) | 0 | LF | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
^^^^^^^^^^^^^INSERT ADDITIONAL PAY ITEMS ABOVE THIS LINE^^^^^^^^^^^^^^^
Task Subtotal |  |  |  |  | 0 |  | 0 |  | 0 | #DIV/0!
TASK 4 - CHANNEL WORK AND STABILIZATION
14 | Geotextile (Erosion Control) (Coir) | 0 | SY | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
15 | Riprap (12 Inch) | 0 | CY | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
16 | Boulders (24" to 36" | 0 | SY | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
17 | Soil Riprap (12 Inch) | 0 | CY | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
18 | Void Filled Riprap (12 Inch) | 0 | CY | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
19 | Soil Wrapped Lift | 0 | LF | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
^^^^^^^^^^^^^INSERT ADDITIONAL PAY ITEMS ABOVE THIS LINE^^^^^^^^^^^^^^^
Task Subtotal |  |  |  |  | 0 |  | 0 |  | 0 | #DIV/0!
TASK 5 - REVEGETATION
20 | Temporary Irrigation | 0 | LS | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
21 | Seeding (Native) (Zone 2) | 0 | AC | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
22 | Seeding (Native) (Zone 3) | 0 | AC | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
23 | Seeding (Native) (Zone 4) | 0 | AC | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
24 | Soil Conditioning (Biosol) | 0 | AC | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
25 | Mulching (Weed Free Straw) | 0 | AC | 1 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
26 | Nursery Stock Container (DRC #10) | 0 | EA | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
27 | Nursery Stock Container (DRC #60) | 0 | EA | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
28 | Cottonwood Cuttings | 0 | EA | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
29 | Willow Cuttings | 0 | EA | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
30 | Cottonwood Cutting Protection | 0 | EA | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
^^^^^^^^^^^^^INSERT ADDITIONAL PAY ITEMS ABOVE THIS LINE^^^^^^^^^^^^^^^
Task Subtotal |  |  |  |  | 0 |  | 0 |  | 0 | #DIV/0!
TASK 6 - GENERAL
31 | Construction Surveying | 0 | L S | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
32 | Construction Surveying (As-builts) | 0 | L S | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
33 | Mobilization | 0 | L S | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
34 | Traffic Control | 0 | L S | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
^^^^^^^^^^^^^INSERT ADDITIONAL PAY ITEMS ABOVE THIS LINE^^^^^^^^^^^^^^^
Task Subtotal |  |  |  |  | 0 |  | 0 |  | 0 | #DIV/0!
TOTALS: |  |  |  |  | 0 |  | 0 |  | 0 | #DIV/0!

## Change Order
PERIODIC ESTIMATE FOR PARTIAL PAYMENT
SUMMARY AND APPROVALS
PERIODIC ESTIMATE NO. # - PERIOD XXXX, 2017 THROUGH XXXXXX, 2017
CONTRACT CHANGE ORDER WORK
CONTRACT CHANGE ORDER WORK |  |  | CONTRACT CHANGE ORDER |  |  |  | THIS PAY PERIOD |  | COMPLETED TO DATE
NO. | DATE | Description Of Change Order | Quantity | Pay Unit | Unit Price | Total Cost | Quantity | Total Cost | Quantity | Total Cost | Percent Complete
(12) | (13) | (14) | (15) | (16) | (17) | (18) | (19) | (20) | (21) | (22) | (23)
TASK #
1 |  |  | 0 | SY | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2 | [5 empty] | 0 |  | 0 |  | 0 | 0%
3 | [5 empty] | 0 |  | 0 |  | 0 | 0%
4 | [5 empty] | 0 |  | 0 |  | 0 | 0%
5 | [5 empty] | 0 |  | 0 |  | 0 | 0%
TOTALS: | [5 empty] | 0 |  | 0 |  | 0 | 0%

## Stored Material
PERIODIC ESTIMATE FOR PARTIAL PAYMENT
SUMMARY AND APPROVALS
PERIODIC ESTIMATE NO. # - PERIOD XXXX, 2017 THROUGH XXXXXX, 2017
SUMMARY OF MATERIAL & EQUIPMENT STORED ON SITE
|  |  |  | MATERIAL OR EQUIPMENT RED'D OR STORED ON SITE THIS PERIOD |  |  | INSTALLED THIS PERIOD |  | NET STORED ON SITE
Bid Item No. | Date Rec'd | Description Of Material or Equipment | Qty Stored from Previous Est. | Quantity | Cost Per Unit | Total Cost | Quantity | Total Cost | Quantity | Total Cost
(24) | (25) | (26) | (27) | (28) | (29) | (30) | (31) | (32) | (33) | (34)
TASK #
1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | [5 empty] | 0 |  | 0 |  | 0
3 | [5 empty] | 0 |  | 0 |  | 0
4 | [5 empty] | 0 |  | 0 |  | 0
5 | [5 empty] | 0 |  | 0 |  | 0
TOTALS: | [5 empty] | 0 |  | 0 |  | 0